## Consultant
Package name | Payment No. | Description | Amount | PAYMENT DATE
|  | Concept Architect - DB | 1550000000
Concept Architect - DB | CA - 1 | Mobilization | 310000000 | 2024-03-01
Concept Architect - DB | CA - 2 | Design brief approved | 290000000 | 2025-10-01
Concept Architect - DB | CA - 3 | Initial concept approved | 400000000 | 2025-10-01
Concept Architect - DB | CA - 4 | Final concept approved | 300000000 | 2025-10-01
Concept Architect - DB | CA - 5 | Approve MP 1-500 | 250000000 | 2026-07-01
| 1 | Concept Architect - AI | 437500000
Concept Architect - AI | CA - AI -1 | Final Payment | 437500000 | 2025-05-01
| 2 | Local Architect | 3874000000
Local Architect | LA - 1 | Mobilization Fee | 774800000 | 2025-10-01
Local Architect | LA - 2 | After the Consultant delivers Architecture Basic Design to the Client | 193700000 | 2026-06-01
Local Architect | LA - 3 | Upon Client approval of full set of Architecture Basic Design Drawings and Documentation, ready for submission to Authority for approval. | 387400000 | 2026-06-01
Local Architect | LA - 4 | Upon Authority’s approval of Basic Design or 6 months from the date the Client approves the Basic Design Documents for submission to Authority. | 193700000 | 2026-08-01
Local Architect | LA - 5 | Upon Client approval of Fire Fighting Appraisal documents ready for submission to Authority for approval (Architecture part). | 193700000 | 2026-08-01
Local Architect | LA - 6 | Upon Authority’s approval of Fire Fighting Appraisal documents or 6 months from the date the Client approves the Fire Fighting Documents for submission to Authority. | 193700000 | 2026-08-01
Local Architect | LA - 7 | After the Consultant delivers Architecture Technical Design to the Client | 193700000 | 2026-08-01
Local Architect | LA - 8 | Upon Client approval of full set of Architecture Technical Design Drawings and Documentation, ready for submission to Authority for Construction Permit. | 193700000 | 2026-08-01
Local Architect | LA - 9 | Upon receipt Construction Permit or 6 months from the date the Client approves the Technical Design Documents for submission to Authority. | 193700000 | 2026-08-01
Local Architect | LA - 10 | Upon the Client award Main contract package or 6 months from the date the Consultant submits tender documents to the Client. (The design documents used in the Tender stage will be the approved Technical design documents) | 387400000 | 2026-09-01
Local Architect | LA - 11 | Upon the full set of Construction Design documents fully updated after Tender and issued for Construction | 193700000 | 2026-09-01
Local Architect | LA - 12 | The Construction / Authorship supervision stage shall be paid to the Consultant by quartely (total 24 months construction from the Commencement date of Main Contract) | 774800000 | 2026-09-01
| 3 | Landscape | 540000000
Landscape | LS - 1 | Mobilization fee | 54000000 | 2025-11-01
Landscape | LS - 2 | Approval concept | 81000000 | 2026-05-01
Landscape | LS - 3 | Approval DD | 162000000 | 2026-07-01
Landscape | LS - 4 | Award Landscape contractor | 81000000 | 2026-10-01
Landscape | LS - 5 | Approval CD | 54000000 | 2026-10-01
Landscape | LS - 6 | Authorship (4 months) | 108000000 | 2027-07-01
| 4 | ID | 5372000000
ID | ID - 1 | Mobilization fee | 780000000 | 2025-09-01
ID | ID - 2 | Show Unit: Upon approval of Initial Concept Design | 98175000
ID | ID - 3 | Show Unit: Upon approval of Final Concept Design | 98175000
ID | ID - 4 | Show Unit: Upon approval of Tender Design Documents, ready for Tender isssuance | 98175000
ID | ID - 5 | Show Unit: Upon awarding Interior Design Contractor and the Consultant issue the Construction Documents | 98175000
ID | ID - 6 | Public Area: Upon approval of Initial Concept Design | 368333333.3333
ID | ID - 7 | Public Area: Upon approval of Final Concept Design | 368333333.3333
ID | ID - 8 | Public Area: Upon submission of Full Schematic Design and already present the Schematic Design to Client | 368333333.3333
ID | ID - 9 | Public Area: Upon approval of Schematic Design | 368333333.3333
ID | ID - 10 | Public Area: Upon the Client approve Tender Design Documents, ready for Tender isssuance | 368333333.3333
ID | ID - 11 | Public Area: Upon awarding Interior Design Contractor and the Consultant issue the Construction Documents | 368333333.3333
ID | ID - 12 | Apartment and Corridor: Upon approval of Initial Concept Design | 411825000
ID | ID - 13 | Apartment and Corridor: Upon approval of Final Concept Design | 411825000
ID | ID - 14 | Apartment and Corridor: Upon the Client approve Tender Design Documents, ready for Tender isssuance | 411825000
ID | ID - 15 | Apartment and Corridor: Upon awarding Interior Design Contractor and the Consultant issue the Construction Documents | 411825000
ID | ID - 16 | Upon submission of 1st Draft 3D renders | 50000000
ID | ID - 17 | Upon submission of 2nd Draft 3D renders | 50000000
ID | ID - 18 | Upon approval for 3D renders | 70000000
ID | ID - 19 | Quartely payment (VND 37,500,000 x 3 months = VND 112,500,000) upon requested by the Client
ID | ID - 20 | Addendum #1 | 172000000
| 5 | Facade Lighting | 326880000
Facade Lighting | FC - 1 | Mobilization fee | 65376000 | 2025-02-01
Facade Lighting | FC - 2 | Upon submit and approved by Client of Concept Design. | 65376000 | 2026-05-01
Facade Lighting | FC - 3 | Upon submit and approved by Client of Design Development. | 81720000
Facade Lighting | FC - 4 | Upon award Façade Lighting Package | 49032000 | 2026-10-01
Facade Lighting | FC - 5 | Upon submit and approved by Client of Construction Development. | 49032000 | 2026-10-01
Facade Lighting | FC - 6 | Upon finish and get approval of the Authorship Supervisor and Commisioning by Client | 16344000 | 2027-09-01
| 6 | Local MEP | 3027300000
Local MEP | MEP - 1 | Mobilization fee/ Phí huy động | 454095000 | 2025-08-01
Local MEP | MEP - 2 | Approval of Concept Deesign | 454095000 | 2026-01-01
Local MEP | MEP - 3 | Upon submittal of a full dossier of Basic Design | 227047500 | 2026-01-01
Local MEP | MEP - 4 | Upon Authoruty’s approval of Schematic Design or Basic Design | 227047500 | 2026-06-01
Local MEP | MEP - 5 | Upon Fire Fighting Appraisal documents ready for submission to Authority for approval. | 227047500 | 2026-05-01
Local MEP | MEP - 6 | Upon Authority’s approval of Fire Fighting Appraisal documents | 227047500 | 2026-05-01
Local MEP | MEP - 7 | Upon Technical Design Documents verified by 3rd Party Verifier / 3rd Party Appraisal, ready for Construction Permit submission. | 302730000 | 2026-07-01
Local MEP | MEP - 8 | Upon receipt Construction Permit | 151365000 | 2026-07-01
Local MEP | MEP - 9 | Upon the full set of Design Development / Technical Design documents, ready for Tender | 151365000 | 2026-08-01
Local MEP | MEP - 10 | Upon the Client award Main contract package | 75682500 | 2026-08-01
Local MEP | MEP - 11 | Upon the Client award MEP package | 75682500 | 2026-10-01
Local MEP | MEP - 12 | Upon the full set of Construction Design documents fully updated after Tender and issued for Construction | 151365000 | 2026-10-01
Local MEP | MEP - 13 | Upon topping out of building structure | 151365000 | 2027-03-01
Local MEP | MEP - 14 | Upon confirmed by MOC and Fire approval for operation | 151365000 | 2027-07-01
| 7 | C&S | 800000000
C&S | CS - 1 | Mobilization | 80000000 | 2024-09-01
C&S | CS - 2 | Approval of Concept Design | 120000000 | 2026-03-01
C&S | CS - 3 | Approval of Basic Design | 120000000 | 2026-07-01
C&S | CS - 4 | Approval of Design Development | 160000000 | 2026-07-01
C&S | CS - 5 | Approval of Tender / Construction docs | 160000000 | 2026-08-01
C&S | CS - 6 | Authorship Supervision (18 months, paid each 6) | 160000000 | 2026-11-01
| 8 | QS | 1000000000
QS | QS - 1 | Mobilization | 100000000 | 2026-02-01
QS | QS - 2 | Submission of Basic Cost plan | 70000000 | 2026-04-01
QS | QS - 3 | Approval of Basic Cost plan | 30000000 | 2026-08-01
QS | QS - 4 | Submission of Design Development CP | 105000000 | 2026-08-01
QS | QS - 5 | Approval of Design Development CP | 45000000 | 2026-08-01
QS | QS - 6 | Award Piling package | 50000000 | 2026-08-01
QS | QS - 7 | Award Main works package | 100000000 | 2026-08-01
QS | QS - 8 | Award MEP package | 50000000 | 2026-09-01
QS | QS - 9 | Award NSC/DC package | 50000000 | 2026-09-01
QS | QS - 10 | After Final Account Piling Works | 50000000 | 2027-10-01
QS | QS - 11 | Construction Admin | 300000000 | 2026-10-01
QS | QS - 12 | Final account | 50000000 | 2027-10-01
| 9 | ID - Ong&Ong | 6474000000
CĂN HỘ MẪU VÀ VĂN PHÒNG BÁN HÀNG
ID - Ong&Ong | ID2 - 1 | Phí huy động | 367250000 | 2026-02-01
ID - Ong&Ong | ID2 - 2 | Sau khi Chủ Đầu Tư phê duyệt Thiết Kế Ý Tưởng | 440700000 | 2026-03-01
ID - Ong&Ong | ID2 - 3 | Sau khi Chủ Đầu Tư phê duyệt Thiết Kế Sơ Bộ | 220350000 | 2026-03-01
ID - Ong&Ong | ID2 - 4 | Sau khi Chủ Đầu Tư phê duyệt Thiết Kế Triển Khai | 440700000 | 2026-04-01
ID - Ong&Ong |  | CHỌN LỰA ĐỒ TRANG TRÍ CHO CĂN HỘ MẪU
ID - Ong&Ong | ID2 - 5 | Ngay khi bắt đầu dịch vụ Chọn lựa đồ trang trí cho Căn hộ mẫu | 90000000 | 2026-04-01
ID - Ong&Ong | ID2 - 6 | Sau khi hoàn thành dịch vụ Chọn lựa đồ trang trí cho Căn hộ mẫu | 90000000 | 2026-07-01
PHỤ LỤC HỢP ĐỒNG SỐ 1
CĂN HỘ ĐIỂN HÌNH
ID - Ong&Ong | ID2 - 7 | Phí huy động | 300000000 | 2026-03-01
ID - Ong&Ong | ID2 - 8 | Sau khi Nhà tư vấn trình Thiết kế triển khai, đầy đủ thành phần hồ sơ để Chủ đầu tư phát hành hồ sơ mời thầu gói thầu hoàn thiện / nội thất | 600000000 | 2026-05-01
ID - Ong&Ong | ID2 - 9 | Sau khi Chủ Đầu Tư phê duyệt Thiết Kế Triển Khai | 600000000 | 2026-09-01
3D
ID - Ong&Ong | ID2 - 10 | Phí huy động | 75000000 | 2026-03-01
ID - Ong&Ong | ID2 - 11 | Sau khi Nhà tư vấn nộp diễn họa hình ảnh nháp lần 1 | 90000000 | 2026-04-01
ID - Ong&Ong | ID2 - 12 | Sau khi Nhà tư vấn nộp diễn họa hình ảnh nháp lần 2 | 90000000 | 2026-04-01
ID - Ong&Ong | ID2 - 13 | Sau khi Chủ đầu tư phê duyệt hình ảnh diễn họa | 45000000 | 2026-04-01
KHU VỰC CÔNG CỘNG
ID - Ong&Ong | ID2 - 14 | Phí huy động | 750000000 | 2026-03-01
ID - Ong&Ong | ID2 - 15 | Sau khi Chủ Đầu Tư phê duyệt Thiết Kế Ý Tưởng | 750000000 | 2026-04-01
ID - Ong&Ong | ID2 - 16 | Sau khi Chủ Đầu Tư phê duyệt Thiết Kế Sơ Bộ | 600000000 | 2026-04-01
ID - Ong&Ong | ID2 - 17 | Sau khi Chủ Đầu Tư phê duyệt Thiết Kế Triển Khai | 900000000 | 2026-09-01
PLHĐ TƯ VẤN TÔ MÀU
ID - Ong&Ong | ID2 - 18 | Phí huy động | 20000000 | 2026-03-01
ID - Ong&Ong | ID2 - 19 | Hoàn thành | 5000000 | 2026-04-01
| 10 | Traffic connection | 6474000000
Traffic connection | TC1 | Phí huy động | 27777777.7778 | 2025-09-01
Traffic connection | TC2 | Hoàn thành | 157407407.4074 | 2026-02-01